# Work break down for Design for tool “Add Layer on slope”

Make a new tool like Dam Soil Profile Tool

Works should be based mostly on existing functionality of DAM, DSL and/or DSoilModel where possible.

Next to the proposal for a fully new tool, it would also be possible to create a special version of DAM UI as a lot of the required functionality is then a given. On the other hand this last option would involve changing DAM UI and DAM Engine as well as the interfacing between these too. And that would make that option expensive. So we will implement as fully new tool as that way we can combine and required functionality within one application.

A new requirement was added that the tool should be a command line tool (so without UI) and that the other tool (“DamSoilProfileTool”) we already developed should also get the possibility to use it as a command line tool.

NOTE: shapefile import will not be supported!

## Steps involving implementation Design

- Create new C# project, implement this in SVN and BuildServer (1 day)

- Create the new command line tool with mock functions (1 day)

AddLayerOnSlope /B /I <Input folder> /O <output folder>

- Copy and reimplement/adapt import functionality for csv files (functionality from DAM-importer in DAM-UI, you must now copy yourself from the csv objects (SurfaceLineRecords) to the surfaceline objects (SurfaceLine2)). Also the location.csv will have 3

- Create a function to add the required offset to the imported surface line which returns the offset as a separate new surface line (new functionality).

- Call DGSMstabDamDll with the 1D or 2D input Geometry and the offset surfaceline. An intermediate geometry (.sti) is created.  (functionality from DamEngine)

- Call DGSMstabDamDll with the intermediate geometry (.sti) (DamEngine) and the original surfaceline. The desired end geometry (.sti) is created. (functionality from DamEngine)

- Add a command line option to the already existing tool “DamSoilProfileTool”

DamSoilProfileTool/B /I <Input folder> /O <output folder>

If we base 3 to 7 on new tool, I foresee:

3) 3 days

4) 1 day

5) 3 days

6) 2 day

7)  1 day

Then we have already spent 2 days on the design and workbreak down and expect to spend another day in other overhead (such as delivery etc.).

So we at least would require 15 days.